## ISO
TOTAL QTP SCENARIOS | 7 |  |  |  | LIST VALUES
QTP SCENARIOS COMPLETED/COVERED | 6 |  |  |  | COMPLETED
TOTAL UNIQUE CUCUMBER SCENARIOS AUTOMATED | 6 |  |  |  | IN-PROGRESS
IN PROGRESS | 0 |  |  |  | PENDING
PENDING | 1 |  |  |  | N/A
TC ID | FEATURE FILE | SCNEARIO NAME IN CUCUMBER | DEVELOPED BY | DATE DEVELOPED | STATUS | COMMENTS
DLMULCH_TC_02 |  |  |  |  | N/A | Need to Perform some action on Poster Add-in tool, which does not support automation
DLMULCH_TC_04 | InStoreOrderingFulfilment.feature | DL-ISOFULFILMENT-01 | SIVA | 2013-09-26 | COMPLETED
DLMULCH_TC_06 | InStoreOrderingFulfilment.feature | DL-ISOFULFILMENT-03 | SIVA | 2013-10-04 | COMPLETED
DLMULCH_TC_07 | InStoreOrderingFulfilment.feature | DL-ISOFULFILMENT-05 | SIVA | 2013-10-09 | COMPLETED
DLMULCH_TC_08 | InStoreOrderingFulfilment.feature | DL-ISOFULFILMENT-04 | SIVA | 2013-10-10 | COMPLETED
DLMULCH_TC_09 | InStoreOrderingFulfilment.feature | DL-ISOFULFILMENT-02 | SIVA | 2013-09-27 | COMPLETED
DLMULCH_TC_10 | InStoreOrderingFulfilment.feature | DL-ISOFULFILMENT-06 | SIVA | 2013-10-15 | COMPLETED

## TDD
TOTAL QTP SCENARIOS | 9 |  |  |  | LIST VALUES
QTP SCENARIOS COMPLETED/COVERED | 8 |  |  |  | COMPLETED
TOTAL UNIQUE CUCUMBER SCENARIOS AUTOMATED | 9 |  |  |  | IN-PROGRESS
IN PROGRESS | 1 |  |  |  | PENDING
PENDING | 0 |  |  |  | N/A
N/A | 0
TC ID | FEATURE FILE | SCNEARIO NAME IN CUCUMBER | DEVELOPED BY | DATE DEVELOPED | STATUS | COMMENTS
TDD_Reg_TC_01 | TDDFulfilment.feature | DL-TDDFULFILMENT-01 | SIVA | 2013-11-28 | COMPLETED
TDD_Reg_TC_02 | TDDFulfilment.feature | DL-TDDFULFILMENT-02 | SIVA | 2013-09-16 | COMPLETED
TDD_Reg_TC_03 | TDDFulfilment.feature | DL-TDDFULFILMENT-04 | SIVA | 2013-09-16 | COMPLETED
TDD_Reg_TC_04 | TDDFulfilment.feature | DL-TDDFULFILMENT-09 | ANGELINE | 2013-11-25 | COMPLETED | UI in Order Confirmation Mail and Order Status and History page needs to be validated manually
TDD_Reg_TC_05 | TDDFulfilment.feature | DL-TDDFULFILMENT-03 | SIVA | 2013-09-13 | COMPLETED
TDD_Reg_TC_08 | TDDFulfilment.feature | DL-TDDFULFILMENT-08 | SIVA | 2013-09-26 | COMPLETED
TDD_Reg_TC_09 | TDDFulfilment.feature | DL-TDDFULFILMENT-05 | SIVA | 2013-09-17 | IN-PROGRESS | BML PRE Orders are not reaching PreOrder queue in CSC, Under Clarification
TDD_Reg_TC_10 | TDDFulfilment.feature | DL-TDDFULFILMENT-06 | SIVA | 2013-09-18 | COMPLETED
Fulfillment attributes verification for DC Alone order having single quantity in turn deferred and in turn sent for cancellation | TDDFulfilment.feature | DL-TDDFULFILMENT-07 | SIVA | 2013-09-19 | COMPLETED

## CAC
TOTAL TC`s | 10 |  |  |  | LIST VALUES
TC`s COMPLETED/COVERED | 8 |  |  |  | COMPLETED
TOTAL UNIQUE CUCUMBER SCENARIOS AUTOMATED | 7 |  |  |  | IN-PROGRESS
IN PROGRESS | 1 |  |  |  | PENDING
PENDING | 0 |  |  |  | N/A
N/A | 1
TC ID | FEATURE FILE | SCNEARIO NAME IN CUCUMBER | DEVELOPED BY | DATE DEVELOPED | STATUS | COMMENTS
TC_IN-397-CLFR_023 | ContactLensReorder.feature | CL-CLFamReorder-12 | Angeline | 2013-10-18 | COMPLETED | Email verification & UI validations should be done by manual regression team
TC_REG_CAC_002 | MixedCartCheckout.feature | SDD-MixedCartCheckout-28 | Angeline | 2013-10-18 | COMPLETED | Email verification & UI validations should be done by manual regression team
TC_REG_CAC_003 | DailyLivingCheckout.feature | DL-CHECKOUT-11 | Ygnash |  | IN-PROGRESS
TC_REG_CAC_005 | PSCCheckout.feature | CHECKOUT-RxCheckout-25 | Thangaraj |  | COMPLETED
TC_REG_CAC_006 | DailyLivingCheckout.feature | DL-CHECKOUT-13 | Fyrose |  | COMPLETED
TC_REG_CAC_015 | DailyLivingCheckout.feature | DL-CHECKOUT-12 | Ygnash | 2013-10-23 | COMPLETED
TC_REG_CAC_016 | DailyLivingCheckout.feature | DL-CHECKOUT-14 | Rukmani | 2013-10-23 | COMPLETED | Order confirmation mail UI verification should be taken care by manual team. XML Logs are not generated as per the EO-25659 hence validation is not covered
TC_REG_CAC_020 |  |  |  |  | N/A | NA,since DB changes require 10-15 minutes for data to be reflected in Accertify
TC_REG_CAC_021 | LoyaltyFulfillment.feature | DL-LoyaltyFulfillment-01 | Thangaraj |  | COMPLETED
TC_REG_CAC_022 | InStoreOrderingFulfilment.feature | DL-ISOFULFILMENT-07 | SIVA | 2013-10-21 | COMPLETED

## CSC
TOTAL SCENARIOS | 22
TOTAL APPLICABLE SCENARIOS | 14 |  |  |  | LIST VALUES
MANUAL SCENARIOS COMPLETED/COVERED | 13 |  |  |  | COMPLETED
TOTAL UNIQUE CUCUMBER SCENARIOS AUTOMATED | 13 |  |  |  | IN-PROGRESS
IN PROGRESS | 1 |  |  |  | PENDING
PENDING | 0 |  |  |  | N/A
Not Applicable | 8
TC ID | FEATURE FILE | SCNEARIO NAME IN CUCUMBER | DEVELOPED BY | DATE DEVELOPED | STATUS | COMMENTS
MCSS_CSC_TC_01 | CSCFulfillmentFlows.feature | CSCF-CSCFulfilment-2 | SARAVANAN M | 2013-10-04 | COMPLETED
MCSS_CSC_TC_02 | N/A | N/A | N/A | N/A | N/A | EPS Related
MCSS_CSC_TC_03 | N/A | N/A | N/A | N/A | N/A | EPS Related
MCSS_CSC_TC_04 | N/A | N/A | N/A | N/A | N/A | Accertify System Related
MCSS_CSC_TC_05 | CSCFulfillmentFlows.feature | CSCF-CSCFulfilment-9 | Angeline | 2013-11-06 | COMPLETED
MCSS_CSC_TC_06 | N/A | N/A | N/A | N/A | N/A | Accertify System Related
MCSS_CSC_TC_07 | CSCFulfillmentFlows.feature | CSCF-CSCFulfilment-8 | SARAVANAN M | 2013-10-29 | COMPLETED
MCSS_CSC_TC_08 | CSCFulfillmentFlows.feature | CSCF-CSCFulfilment-10 | SARAVANAN M | 2013-11-05 | COMPLETED
MCSS_CSC_TC_09 | N/A | N/A | N/A | N/A | N/A | Accertify System Related
MCSS_CSC_TC_10 | N/A | N/A | N/A | N/A | N/A | Accertify System Related
MCSS_CSC_TC_11 | CSCFulfillmentFlows.feature | CSCF-CSCFulfilment-7 | SARAVANAN M | 2013-10-29 | COMPLETED
MCSS_CSC_TC_12 | CSCFulfillmentFlows.feature | CSCF-CSCFulfilment-5 | SARAVANAN M | 2013-10-28 | COMPLETED
MCSS_CSC_TC_13 | CSCFulfillmentFlows.feature | CSCF-CSCFulfilment-1 | SARAVANAN M | 2013-09-24 | COMPLETED
MCSS_CSC_TC_14 | N/A | N/A | N/A | N/A | N/A | Accertify System Related
MCSS_CSC_TC_16 | N/A | N/A | N/A | N/A | N/A | EPS Related
MCSS_CSC_TC_17 | CSCFulfillmentFlows.feature | CSCF-CSCFulfilment-11 | SARAVANAN M | 2013-11-08 | COMPLETED
|  | CSCF-CSCFulfilment-13 | THANGARAJ R | 2013-11-13 | COMPLETED
MCSS_CSC_TC_18 | CSCFulfillmentFlows.feature | CSCF-CSCFulfilment-14 | Angeline | 2013-11-12 | COMPLETED
MCSS_CSC_TC_19 | CSCFulfillmentFlows.feature | CSCF-CSCFulfilment-6 | Angeline | 2013-11-13 | COMPLETED
MCSS_CSC_TC_20 | CSCFulfillmentFlows.feature | CSCF-CSCFulfilment-15 | Angeline | 2013-10-24 | IN-PROGRESS | Scripting Completed but due to Orders Status change issue script is getting failed hence keeping it in IN progress
MCSS_CSC_TC_21 | CSCFulfillmentFlows.feature | CSCF-CSCFulfilment-4 | SIVA | 2013-10-28 | COMPLETED
MCSS_CSC_TC_22 | CSCFulfillmentFlows.feature | CSCF-CSCFulfilment-3 | Angeline | 2013-10-29 | COMPLETED
MCSS_CSC_TC_23 | CSCFulfillmentFlows.feature | CSCF-CSCFulfilment-12 | SARAVANAN M | 2013-11-15 | COMPLETED